## Sample Preparation Schedule
Person in Charge
Milestone
| Start work |  | － | ▽
| Assign roles to the team members |  | － |  | ▽
| Finish arranging venue |  | － |  |  | ▽
| Finish preparing game material |  | － |  |  |  | ▽
| Determine participants (guideline: finalize as soon as capacity is reached) |  | － |  |  |  |  | ▽
| Confirm event-day roles and preparations |  | － |  |  |  |  | ▽
| Complete advance preparations |  | － | [5 empty] | ▽
| Conduct training |  | － | [6 empty] | ▽
2. Schedule until Training
2.1 Example of Preparation Schedule
| 2.1.1 Review the Program |  | Supervisor
| 2.1.2 Identify Team Members and Assign Roles and Responsibilities |  | Supervisor & members
| 2.1.3 Prepare the Lecture Material (Material, Handouts, etc.) and Game Tools |  | Operations and game team leaders and members
|  | Review lecture material & practice presentation | (Supervisor or) operations team leader
|  | Review and prepare Game of Choice material | Game team leader & members
2.1.4 CSR/Sustainable Procurement Training Planning and Operations Manual
|  | Review | Supervisor & operations team
|  | Consultation & editing | Supervisor & operations team
| 2.1.5 Arrange the Venue |  | Supervisor and/or operations team leader
| 2.1.6 Announce Event (Accept Applications, Create Participant List) |  | Supervisor and/or operations team leader
| 2.1.7 Pre-Test Game by the Team Members |  | Game team leader & members of both teams
|  | Game of Choice (dotted line: preparation） | Preparation: Game team
| 2.1.8 Confirm Event-Day Roles and Arrangement |  | (Supervisor &) operations team
| 2.1.9 Prepare the Emcee's Script |  | Operations team leader
| 2.1.10 Prepare the Welcoming Remarks |  | Supervisor
| 2.1.11 Prepare the Questionnaire |  | Operations team
Other